## A
S C O P E D E F I N I T I O N M A T R I X
DESCRIPTION
|  |  |  | Revision | Fronr-End Engineering (FEED) |  | Detailed Engineering & Procurement |  |  | Construction, Commissioning & Turnover
LEGEND:
|  | XXX |  | Client
F = Fluor
|  | C SC= Client Subcontractor | [11 empty] | COMMENTS
F SC = Fluor Subcontractor
EPC = EPC Contractor
S/SC = Supplier / Construction Subcontractor
A = Approve I = Input
|  | P = Primary R = Review |  |  | XXX | F | XXX | EPC | S/SC | XXX | CSC | EPC | S/SC
S = Secondary N/A = Not Applicable
TABLE OF CONTENTS
| 1 |  | GENERAL ENGINEERING
| 2 |  | PROCESS ENGINEERING
| 3 |  | ENVIRONMENTAL / HEALTH / SAFETY
| 4 |  | MECHANICAL ENGINEERING
| 5 |  | CIVIL
| 6 |  | STRUCTURAL
| 7 |  | BUILDING ARCHITECTURAL
| 8 |  | HEATING, VENTALATION, AND AIR CONDITIONING (HVAC)
| 9 |  | PLUMBING
| 10 |  | FIREPROTECTION
| 11 |  | AUXILIARY SYSTEMS
| 12 |  | PIPING
| 13 |  | PAINTING, INSULATION & FIREPROOFING
| 14 |  | ELECTRICAL
| 15 |  | INSTRUMENTATION & CONTROLS
| 16 |  | PROJECT MANAGEMENT & SUPPORT
| 17 |  | PROJECT CONTROLS
| 18 |  | TECHNICAL DOCUMENT CONTROL
| 19 |  | PROJECT INFORMATION MANAGEMENT
| 20 |  | MATERIALS MANAGEMENT
| 21 |  | CONTRACT ADMINISTRATION
| 22 |  | PERMITTING
| 23 |  | CONSTRUCTION SUPPORT
| 24 |  | CONSTRUCTION MANAGEMENT SERVICES & CONSTRUCTION
| 25 |  | COMMISSIONING & STARTUP
1.0 GENERAL ENGINEERING
| 1.1 | Scope of Facilities |  |  | I/R/A | P | I/R/A | P | R | I/A | R | P | R
| 1.2 | Scope of Services |  |  | I/R/A | P | I/R/A | P | R | I/A | R | P | R
| 1.3 | Project Checklists | bar: P P
| 1.4 | Discipline Checklists | bar: P P
2.0 PROCESS ENGINEERING
| 2.1 | Process Descriptions and Operating Philosophy
| 2.2 | Process Conditions
|  | a. | Process Design Basis |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Process Batch Data |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Process Physical Properties |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Physical Properties Data Book
|  | d. | Utility Design Conditions |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | e. | Chemical and Catalyst Summary |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | f. | Physical Properties Data Bank |  | I/R/A I/R/A: P; P P: R; I/R/A I/R/A: I/R/A; P P: P | The physical properties data bank from ASPEN
|  | g. | Process Description with Chemistry |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | h. | Specifications of Raw Materials / Intermediates / Products |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | i. | Raw Matls/Intermediates/Product Storage Requirements |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | j. | Equipment Design Criteria |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 2.3 | Basic Operating Description
|  | a. | Basic Operating Philosphy |  | I/R/A I/R/A: P; P P: I/R; I/R/A I/R/A: P; P P: I/R; I/A I/A: P
|  | b. | Start-up & Shut-down Philosophy |  | I/R/A I/R/A: P; P P: I/R; I/R/A I/R/A: P; P P: I/R; I/A I/A: P
|  | c. | Emergency Shut-down Philosophy |  | I/R/A I/R/A: P; P P: I/R; I/R/A I/R/A: P; P P: I/R; I/A I/A: P
| 2.4 | Process Control Description
|  | a. | Process Areas |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Utilities |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 2.5 | Process Block Flow Diagram |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 2.6 | Process Flow Diagrams (PFDs)
|  | a. | Conceptual PFDs
|  |  | - | Process Areas
-- PFD's
-- Heat and Material Balance
|  |  | - | Environmental & Utilities
-- PFD's
-- Heat and Material Balance
|  | b. | Approved For Design PFDs
|  |  | - | Process Areas
|  |  |  | -- PFDs | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- Utility Summary | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities
|  |  |  | -- PFDs | I/R/A I/R/A: R/A; P P: P; I/R/A I/R/A: R/A; P P: P
|  |  |  | -- Utility Summary | I/R/A I/R/A: R/A; P P: P; I/R/A I/R/A: R/A; P P: P
| 2.7 | Engineering Flow Diagrams (P&IDs)
|  | a. | Approved For Design P&IDs
|  |  | - | Process Areas | I/R/A I/R/A: R/A; P P: P; I/R/A I/R/A: R/A; P P: P; R R: I
|  |  | - | Environmental & Utilities | I/R/A I/R/A: R/A; P P: P; I/R/A I/R/A: R/A; P P: P; R R: I | Packaged units to be shown with a boundary only. No details shown within the boundary for packaged units.
|  |  | - | Demolition & Relocation P&IDs | I/R/A I/R/A: R/A; P P: P; R R: I | None foreseen during the FEED.
|  |  | - | Conduct Review | I/R/A I/R/A: R/A; P P: P; I/R/A I/R/A: R/A; P P: P; R R: I
|  | b. | Approved for Construction P&IDs
|  |  | - | Process Areas |  |  | R/A | P | I | R/A | I | P | I
|  |  | - | Environmental & Utilities |  |  | R/A | P | I | R/A | I | P | I
|  |  | - | Demolition & Relocation P&IDs |  |  | R/A | P | I | R/A | I | P | I
| 2.8 | Utility Flow Diagrams (UFDs)
|  | a. | Approved For Design UFDs
|  |  | - | Process Areas | I/R/A I/R/A: R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: R/A; P P: P
|  |  | - | Demolition & Relocation UFDs | [9 empty] | None foreseen during the FEED.
|  |  | - | Conduct Review | I/R/A I/R/A: R/A; P P: P
|  | b. | Approved for Construction UFDs
|  |  | - | Process Areas |  |  | R/A | P | I | R/A | I | P | I
|  |  | - | Environmental & Utilities |  |  | R/A | P | I | R/A | I | P | I
|  |  | - | Demolition & Relocation UFDs |  |  | R/A | P | I | R/A | I | P | I
| 2.9 | Update P&IDs for Vendor Information
|  | a. | Process Areas |  |  |  | R/A | P | I | R/A | I | P | I
|  | b. | Environmental & Utilities |  |  |  | R/A | P | I | R/A | I | P | I
|  | c. | Infrastructure |  |  |  | R/A | P | I | R/A | I | P | I
| 2.1 | Material Handling / Logistics Plan |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 2.11 | Detailed Process Calcualtions
|  | a. | References |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | b. | Materials Inventory and Usage Summary |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | c. | Utilities Consumption & Flows |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P | Not a FEED deliverable…available for XXX review.
|  | d. | Pinch Study | [10 empty] | Minimual value….not part of FEED Scope.
|  | e. | Analysis of Energy Conservation Opportunities | [10 empty] | Minimual value….not part of FEED Scope.
| 2.12 | Hydraulic Calculations
|  | a. | Pump Calculations
|  |  | - | Process Areas | [9 empty] | Not a FEED deliverable…available for XXX review. | bar: I/R/A I/R/A to P P
|  |  | - | Environmental & Utilities | [9 empty] | Not a FEED deliverable…available for XXX review. | bar: I/R/A I/R/A to P P
|  | b. | Process Line Summary
|  |  | - | Process Areas | [9 empty] | Not a FEED deliverable…available for XXX review. | bar: I/R/A I/R/A to P P
|  |  | - | Environmental & Utilities | [9 empty] | Not a FEED deliverable…available for XXX review. | bar: I/R/A I/R/A to P P
| 2.13 | Equipment List Input
|  | a. | All Process, Utility, & Environmental Equipment | bar: I/R/A I/R/A to P P; I/A I/A; P P
|  | b. | Equipment Numbers | bar: I/R/A I/R/A to P P; I/A I/A; P P
|  | c. | Equipment Data | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 2.14 | Equipment Selection and Sizing
|  | a. | Process Areas |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: R/A; P P: P
|  | b. | Environmental & Utilities |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: R/A; P P: P
|  | c. | Infrastructure |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: R/A; P P: P
| 2.15 | Process Equipment Data Sheets
|  | a. | Critical Equipment |  | I/R/A I/R/A: R/A; P P: P; I/R/A I/R/A: R/A; P P: P
|  | b. | Non-Critical Equipment |  | I/R/A I/R/A: R; P P: P; I/R/A I/R/A: R/A; P P: P
| 2.16 | Piping Line List Input
|  | a. | Design Temperatures and Pressures | bar: I/R/A I/R/A to P P
|  | b. | Normal Operating Temperatures and Pressures | bar: I/R/A I/R/A to P P
|  | c. | Upset Conditions | bar: I/R/A I/R/A to P P
|  | d. | Heat Tracing Requirements | bar: I/R/A I/R/A to P P
|  | e. | Metallurgical Requirments | bar: I/R/A I/R/A to P P
| 2.17 | Instrumentation and Controls Input
|  | a. | Control Valve Specifications
|  |  | - | Process Areas | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | b. | Flow Element Specifications
|  |  | - | Process Areas | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | c. | Analyzer Specifications
|  |  | - | Process Areas | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | d. | Auxiliary System Specifications
|  |  | - | Process Areas | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | e. | Process Interlock Description / Matrix
|  |  | - | Process Areas | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | f. | Others
|  |  | - | Process Areas | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
| 2.18 | Relief System
|  | a. | Design Philosophy |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Relief Load Summary
|  |  | - | Process Areas | [9 empty] | Does not apply with present scope.
|  |  | - | Environmental & Utilities | [9 empty] | Does not apply with present scope.
|  | c. | Unit Relief System Needs
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | d. | Relief Valve Specifications
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | e. | Relief Valve Sizes
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary sizing during FEED.
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary sizing during FEED.
|  | f. | Line Sizing
|  |  | - | Process Areas | [9 empty] | Preliminary sizing during FEED. | bar: P P; P P
|  |  | - | Environmental & Utilities | [9 empty] | Preliminary sizing during FEED. | bar: P P; P P
| 2.19 | Environmental Loads & Treatment
|  | a. | Required Regulations | bar: I/R/A I/R/A to P P
|  | b. | Wastewater Collection
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Wastewater Treatment
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | d. | Solid Waste
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | e. | Air Emissions
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | f. | Noise Compliance
|  |  | - | Process Areas | I/R/A I/R/A: I/R/A; P P: P | Requirements established during FEED
|  |  | - | Environmental & Utilities | I/R/A I/R/A: I/R/A; P P: P | Requirements established during FEED
| 2.2 | Systems Turnover Philosophy |  |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | I
| 2.21 | Review Vendor Data for Compliance to Process Conditions
|  | a. | Process Areas |  | I/R/A I/R/A: I/R; P P: P
|  | b. | Environmental & Utilities |  | I/R/A I/R/A: I/R; P P: P
| 2.22 | As-Built Drawings (Reference Section 23.0 below) |  |  | I/A I/A: R/A; P P: P
3.0 ENVIRONMENTAL / HEALTH / SAFETY
| 3.1 | Design Basis to IFD | bar: I/R/A I/R/A to P P
| 3.2 | Environmental Impact Study
|  | a. | Preliminary Environmental Impact Study | bar: I/R/A I/R/A to P P
|  | b. | Detailed Environmental Impact Study | bar: I/R/A I/R/A to P P
| 3.3 | Quantitative Risk Analysis (QRA)
|  | a. | Preliminary Quantitative Risk Analysis | bar: I/R/A I/R/A to P P
|  | b. | Detailed Quantitative Risk Analysis | bar: I/R/A I/R/A to P P
| 3.4 | Material Safety Data Sheets (MSDS)
|  | a. | Raw Materials | bar: I/R/A I/R/A; I/R/A I/R/A; I/A I/A
|  | b. | Intermediates | bar: I/R/A I/R/A; I/R/A I/R/A; I/A I/A
|  | c. | Products | bar: I/R/A I/R/A; I/R/A I/R/A; I/A I/A
|  | d. | Auxiliary Materials | bar: I/R/A I/R/A; I/R/A I/R/A; I/A I/A
|  | e. | Construction Chemicals & Gases |  | I/A I/A: I/R/A; P P: S; R R: P
| 3.5 | Health & Safety Requirements
|  | a. | XXX Corporate Requirements | bar: I/R/A I/R/A to P P; I/A I/A; P P
|  | b. | Local / State / Federal Requirements | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 3.6 | Noise Protection Requirements
|  | a. | Preliminary Noise Protection Requirements |  | I/R/A I/R/A: I/R/A; P P: P | Requirements listed in the Scope of Facilities.
|  | b. | Detailed Noise Protection Study | bar: I/R/A I/R/A to P P
|  | c. | Production Noise Protection Field Survey |  | I/A I/A: I/R/A; R R: P
| 3.7 | Waste Reduction Plan
|  | a. | Conceputal Waste Reduction Plan
|  | b. | Final Waste Reduction Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 3.8 | Emission Reduction Plan
|  | a. | Conceptual Emission Reduction Plan
|  | b. | Final Emission Reduction Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 3.9 | Energy Conservation Study
|  | a. | Conceptual Energy Conservation Study
|  | b. | Final Energy Conservation Study | [10 empty] | CEP scope item only.
| 3.1 | Process Hazard Analysis (PHA)
|  | a. | "Dow Indexing"
|  | b. | Chemical Interaction Matrix |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | "What If" PHA |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Hazard & Operability Study (HAZOP) | [10 empty] | Facilitated by XXX | bar: I/R/A I/R/A to P P
|  | e. | Listing of "Safety Critical" Equipment & Controls | [10 empty] | Facilitated by XXX | bar: I/R/A I/R/A to P P
4.0 MECHANICAL ENGINEERING
| 4.1 | Mechanical Specifications for:
|  | a. | Process Equipment
|  |  | - | Approved for Inquiry
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Approved for Purchase
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Utility Equipment
|  |  | - | Approved for Inquiry
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Approved for Purchase
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Packaged Equipment
|  |  | - | Approved for Inquiry
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Approved for Purchase
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Spare Parts Requirements
|  |  | - | Approved for Inquiry
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | P P: P; I/R/A I/R/A: I/R/A; P P: P | Narrative required to convey general spare parts reqmts.
|  |  | - | Approved for Purchase
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Equipment Installation |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 4.2 | Project Equipment List
|  | a. | CEP Project Equipment List | [10 empty] | CEP Equipment List to provide a detailed one line description.
|  | b. | Approved For Design |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Approved For Construction |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 4.3 | Mechanical Equipment Specification Data Sheets or Drawings for Quotation and Purchase
|  | a. | Process Data Sheets with Mechanical Data
|  |  | - | Approved for Inquiry
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P | Preliminary only during FEED.
|  |  | - | Approved for Purchase
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Develop Preliminary Sketches or Catalog Cut Sheets for Equipment Arrangement |  | I/R/A I/R/A: I/R; P P: P
|  | c. | Preliminary Fabricated Equipment Drawings
|  |  | - | Reactors | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Critical Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Non-Critical Equipment | [9 empty] | Removed from FEED Scope….part of EPC Scope
| 4.4 | Equipment Procurement and Fabrication Activities
|  | a. | Technical Evaluations of Vendor Quotations
|  |  | - | Process Areas
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Utilities
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Review Vendor Drawings & Data for Compliance to Specifications
|  |  | - | Process Areas
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED scope due to cash flow
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Utilities
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED scope due to cash flow
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  | c. |  | Resolve Technical issues during fabrication
|  |  | - | Process Areas
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED scope
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Utilities
|  |  |  | -- Long Lead Equipment | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED scope
|  |  |  | -- All Other Equipment | I/R/A I/R/A: I/R/A; P P: P
| 4.5 | Spare Parts Coordination
|  | a. | Coordinate Spare Parts Recommendations | [10 empty] | See item 4.2d. Narrative only required.
|  | b. | Issue Supplier Recommendations:
|  |  | - | Const. / Comm. Spares | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Capital (Investment) Spares | I/R/A I/R/A: I/R/A; P P: P
| 4.6 | Lubrication Requirements Summary |  |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED scope.
| 4.7 | Mechanical Equipment Installation and Checkout |  |  | I/A I/A: I/R/A; P P: I/R/A; R R: P | Subcontractor is responsible for equipment installation and checkout.
| 4.8 | As-Built Drawings (Reference Section 23.0 below) |  |  | I/A I/A: I/R/A; P P: I/R/A; R R: P | Equipment supplier is primary.
5.0 CIVIL
| 5.1 | Civil Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 5.2 | Site Survey
|  | a. | Develop Requirements |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Survey Contractor Technical Evaluation |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Develop Survey Data and Report | [10 empty] | Survey Contractor
|  | d. | Review Survey Data and Report | bar: I/R/A I/R/A to P P
|  | e. | Review and Establish Plant Design Datum | bar: I/R/A I/R/A to P P
| 5.3 | Soils/Geotechnical Report
|  | a. | Develop Requirements |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Geotechnical Contractor Technical Evaluation |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Develop Soils/Geotech Data | [10 empty] | Geotechnical Contractor
|  | d. | Review Soils/Geotech. Report | bar: I/R/A I/R/A to P P
|  | e. | Review and Establish Foundation Design Criteria | bar: I/R/A I/R/A to P P
| 5.4 | Site Civil Works
|  | a. | Site Utilization Plan
|  |  | - | Site Utilization Plan to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Site Utilization Plan to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Site Plan Drawings
|  |  | - | Site Plan Drawings to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Site Plan Drawings to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Roads & Paving Design / Drawings to IFC
|  | d. | Grading & Drainage Design / Drawings to IFC
|  | e. | Site Civil Works Specifications
|  |  | - | Site Civil Works Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Site Civil Works Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
| 5.5 | Underground Civil Works
|  | a. | Storm Sewer System Design / Drawings IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Sanitary Sewer System Design / Drawings IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Process Sewer System Design / Drawings IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Site Fire Protection Drawings IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Site Water Distribution Drawings IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | f. | U.G. Civil Works Specifications
|  |  | - | U.G. Civil Works Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | U.G. Civil Works Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
| 5.6 | As-Built Drawings (Reference Section 23.0 below)
6.0 STRUCTURAL
| 6.1 | Structural Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 6.2 | General Specifications - Structural
|  | a. | Concrete Specifications
|  |  |  | Concrete Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  |  | Concrete Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Structural Steel Specifications
|  |  |  | Structural Steel Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  |  | Structural Steel Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
| 6.3 | Concrete Foundations & Structures
|  | a. | Concrete Foundations - Engr. Design |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary sketches only for estimate.
|  | b. | Concrete Structures - Engr. Design |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary sketches only for estimate.
|  | c. | Concrete Design Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Foundation Location Control Plans
|  |  | - | Foundation Location Control Plans to IFD | I/R/A I/R/A: I/R/A; P P: P | Not enough vendor data available to perform this task. Eliminated from FEED scope.
|  |  | - | Foundation Location Control Plans to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Concrete Material Takeoff |  | I/R/A I/R/A: I/R/A; P P: P
|  | f. | Concrete and Reinforcing Steel Procurement |  | I/R/A I/R/A: I/R/A; P P: P
| 6.4 | Structural Steel
|  | a. | Structural Steel - Engr. Design |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary only
|  | b. | Structural Steel Modeling in 3D Model |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary only
|  | b. | Structural Steel - Design Drawings
|  |  | - | Structural Steel Drawings for RFQ | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Structural Steel Drawings to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Structural Platform & Ladder Designs
|  |  | - | Structural Platform & Ladder Drawings for RFQ | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Structural Platform & Ladder Drawings to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Steel Material Takeoff (Total Quantities by weight categories) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Estimate basis documentation.
|  | e. | Structural Steel RFQs |  | I/R/A I/R/A: I/R/A; P P: P
|  | f. | Structural Steel Procurement |  | I/R/A I/R/A: I/R/A; P P: P
|  | g. | Steel Delivery Tracking |  | I/R/A I/R/A: I/R; P P: P
| 6.5 | As-Built Drawings (Reference Section 23.0 below)
7.0 BUILDING ARCHITECTURAL
| 7.1 | Architectural Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 7.2 | Architectural Work -- New Buildings
|  | a. | Building Definition (Design Basis Criteria) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in Scope of Facilities
|  | b. | Building Layout / Design |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary floor plans and elevations only.
|  | c. | PDS Model |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Building outlines provided in PDS model only.
|  | d. | Regulatory Approvals |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope. Part of FEED permitting effort.
|  | e. | Bldg Structural Design (Calcs & Sketches) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary only.
|  | f. | Production Architectural Drawings & Details
|  |  | - | Architectural Drawings & Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Preliminary floor plans and elevations only. See 7.1 b.
|  |  | - | Architectural Drawings & Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | g. | Vendor/Subcontractor Data/Dwg Reviews |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope….part of EPC Scope.
|  | h | Architectural Narrative Specifications
|  |  | - | Architectural Narrative Specificatons to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Architectural Narrative Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
| 7.3 | Architectural Work -- Existing Buildings
|  | a. | Building Definition (Design Basis Criteria) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in Scope of Facilities
|  | b. | Building Layout / Design |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary floor plans and elevations only.
|  | c. | PDS Model |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope.
|  | d. | Regulatory Approvals |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope. Part of FEED permitting effort.
|  | e. | Bldg Structural Design (Calcs & Sketches) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary only.
|  | f. | Production Architectural Drawings & Details
|  |  | - | Architectural Drawings & Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Preliminary floor plans and elevations only. See 7.2 b.
|  |  | - | Architectural Drawings & Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | g. | Vendor/Subcontractor Data/Dwg Reviews |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope….part of EPC Scope.
|  | h | Architectural Narrative Specifications
|  |  | - | Architectural Narrative Specificatons to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs with underwriters approval for FEED.
|  |  | - | Architectural Narrative Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
| 7.4 | As-Built Drawings (Reference Section 23.0 below)
8.0 HEATING, VENTALATION & AIR CONDITIONING (HVAC)
| 8.1 | HVAC Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 8.2 | Building Utility Block Loads |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 8.3 | Energy Recovery Study |  |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope
| 8.4 | HVAC Zone Diagrams
|  | a. | HVAC Zone Diagrams to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope
|  | b. | HVAC Zone Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.4 | HVAC Air Flow Diagrams | HVAC Air Flow Diagrams
|  | a. | HVAC Air Flow Diagrams to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope
|  | b. | HVAC Air Flow Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.6 | HVAC Equipment Lists
|  | a. | HVAC Equipment Lists to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | HVAC Equipment Lists to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.7 | HVAC Equipment Layout
|  | a. | HVAC Equipment Layout to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope. Reserve space on plot / model only.
|  | b. | HVAC Equipment Layout to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.8 | HVAC Specifications
|  | a. | HVAC Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | HVAC Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.9 | HVAC Installation Specifications
|  | a. | HVAC Installation Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | HVAC Installation Specfications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.10 | Duct Plans, Sections, Details & Schedules
|  | a. | Duct Plans, Sections, Details & Schedules to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope.
|  | b. | Duct Plans, Sections, Details & Schedules to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.11 | Air Balance Summary
|  | a. | Air Balance Summary to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope.
|  | b. | Air Balance Summary to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.12 | Building Cooling Load Calculations
|  | a. | Preliminary Building Cooling Load Calculations |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | b. | Final Building Cooling Load Calculations |  | I/R/A I/R/A: I/R; P P: P
| 8.13 | Technical Request for Quotations - Major Equip. |  |  | I/R/A I/R/A: I/R; P P: P
| 8.14 | Technical Bid Evaluations & Procurement - Major Equipment |  |  | I/R/A I/R/A: I/R; P P: P
| 8.15 | HVAC Pressurization Diagrams
|  | a. | HVAC Pressurization Diagrams to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from the FEED Scope… Detailed EPC Scope.
|  | b. | HVAC Pressurization Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 8.16 | PDS Model Development | bar: P P; P P
| 8.17 | Shop Drawing Review | bar: P P
| 8.19 | Material Takeoffs | [11 empty] | Material takeoff by installation contractors. | bar: R R
| 8.20 | Installation and Checkout |  |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 8.21 | As-Built Drawings (Reference Section 23.0 below)
9.0 PLUMBING
| 9.1 | Plumbing Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 9.2 | PDS Model Development |  |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED scope.
| 9.3 | Riser Diagram
|  | a. | Riser Diagram to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Philosophy to be conveyed in Scope of Facilities.
|  | b. | Riser Diagram to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.4 | Under Slab Piping Drawings
|  | a. | Under Slab Piping Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope to be determined.
|  | b. | Under Slab Piping Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.5 | Roof Drainage Drawings
|  | a. | Roof Drainage Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Philosophy to be conveyed in Scope of Facilities.
|  | b. | Roof Drainage Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.6 | Plumbing Plans & Details
|  | a. | Plumbing Plans & Details to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope … part of EPC Scope.
|  | b. | Plumbing Plans & Details to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.7 | Plumbing Fixture Specifications
|  | a. | Plumbing Fixture Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Plumbing Fixture Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.8 | Plumbing Installations Specifications
|  | a. | Plumbing Installation Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Plumbing Installation Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.9 | Plumbing Detail Drawings
|  | a. | Plumbing Detail Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope … part of EPC Scope.
|  | b. | Plumbing Detail Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 9.10 | Plumbing Material Takeoffs | [11 empty] | Material takeoffs by construction contractors. | bar: R R
| 9.11 | Installation and Checkout |  |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 9.12 | As-Built Drawings (Reference Section 23.0 below)
10.0 FIRE PROTECTION
| 10.1 | Fire Protection & Gas Alarm Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs with underwriters approval for FEED.
| 10.2 | System & Alarm Definitions |  |  | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope … part of EPC Scope.
| 10.3 | Fire Protection & Alarms Drawings
|  | a. | Fire Protection & Alarm Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs with underwriters approval for FEED.
|  | b. | Fire Protection & Alarm Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 10.4 | Fire Protection System & Alarm Specifications
|  | a. | Fire Protection System & Alarm Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs with underwriters approval for FEED.
|  | b. | Fire Protection System & Alarm Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 10.5 | Fire Protection Material Takeoffs | [11 empty] | Material takeoffs by construction contractors. | bar: R R
| 10.6 | Installation and Checkout |  |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 10.7 | As-Built Drawings (Reference Section 23.0 below)
11.0 AUXILIARY SYSTEMS
| 11.1 | Auxiliary Systems Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs with underwriters approval for FEED.
| 11.2 | Communication System (Plant Paging, Public Address, Telephone)
|  | a. | Specification (IBL Devices Only)
|  |  | - | Communication System Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Communication System Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Plans and Details to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Connection Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Communication System Material Takeoffs | [10 empty] | Material takeoffs by construction constractors. | bar: R R
|  | e. | Installation and Checkout |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 11.3 | Voice & Data
|  | a. | Voice & Data Specifications
|  |  | - | Voice & Data Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Voice & Data Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Wiring Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Voice & Data Material Takeoffs | [10 empty] | Material takeoffs by construction constractors. | bar: R R
|  | d. | Installation and Checkout |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 11.4 | Fire Alarm System
|  | a. | Specification (IBL Devices Only)
|  |  | - | Fire Alarm System Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Fire Alarm System Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Fire Alarm Plans & Details |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Schematics & Connection Diagrams |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Fire Alarm Material Takeoffs | [10 empty] | Material takeoffs by construction constractors. | bar: R R
|  | e. | Installation and Checkout |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 11.5 | Close Circuit Television
|  | a. | Specification (IBL Devices Only)
|  |  | - | Close Circuit Television Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Close Circuit Television Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Close Circuit Television Plans & Details |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Schematics & Connection Diagrams |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Close Circuit Television Material Takeoffs | [10 empty] | Material takeoffs by construction constractors. | bar: R R
|  | e. | Installation and Checkout |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 11.6 | Site Security
|  | a. | Specification (IBL Devices Only)
|  |  | - | Site Security Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Site Security Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Site Security Plans & Details |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Schematics & Connection Diagrams |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Site Security Material Takeoffs | [10 empty] | Material takeoffs by construction constractors. | bar: R R
|  | e. | Installation and Checkout |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 11.6 | As-Built Drawings (Reference Section 23.0 below)
12.0 PIPING
| 12.1 | Piping Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 12.2 | Narrative Piping Specifications
|  | a. | Narrative Piping Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Need to include Hot Tap Spec. Listing of XXX specs in Scope of Facilities. Fluor to develop unique specs during FEED.
|  | b. | Narrative Piping Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.3 | Piping Welding Specifications
|  | a. | Piping Welding Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Listing of XXX specs in Scope of Facilities. Fluor to develop unique specs during FEED.
|  | b. | Piping Welding Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.4 | Piping Standards Drawings
|  | a. | Piping Standards Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Maximum use of existing XXX Standard Drawings. Fluor to develop for unique requirements.
|  | b. | Piping Standards Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.5 | Piping Line List
|  | a. | Piping Line List to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Piping Line List to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.6 | Piping Material Specification
|  | a. | Line Class Index
|  |  | - | Line Class Index to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Line Class Index to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Piping Material Specifications
|  |  | - | Piping Material Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Piping Material Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Piping Commodity Catalog
|  |  | - | Piping Commodity Catalog to IFD | I/R/A I/R/A: I/R/A; P P: P | Eliminated from FEED Scope … part of EPC Scope.
|  |  | - | Piping Commodity Catalog to IFC | bar: P P
| 12.7 | Develop Piping Electronic Reference Data Bases
|  | a. | Piping Commodity Data | [10 empty] | Eliminated from FEED Scope … part of EPC Scope. | bar: P P
|  | b. | Piping Job Spec. Database | [10 empty] | Eliminated from FEED Scope … part of EPC Scope. | bar: P P
|  | c. | Description / Label Libraries | [10 empty] | Eliminated from FEED Scope … part of EPC Scope. | bar: P P
|  | d. | Piping Dimensional Tables | [10 empty] | Eliminated from FEED Scope … part of EPC Scope. | bar: P P
| 12.8 | Piping Specialty Item List
|  | a. | Piping Specialty Item List to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Speciality Items to reference XXX standards with exceptions listed.
|  | b. | Piping Specialty Item List ot IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.9 | Equipment Layout Studies | bar: P P; P P
| 12.10 | Plot Arrangement
|  | a. | Overall Plot Plan
|  |  | - | Overall Plot Plan to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Overall Plot Plan to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. |  | Unit Plot Plans
|  |  | - | Unit Plot Plans to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Unit Plot Plans to IFC | I/R/A I/R/A: I/R/A; P P: P
| 12.11 | Piping Tie-In List
|  | a. | Piping Tie-In List to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Piping Tie-In List to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.12 | Design Model
|  | a. | Design Model Review Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Electronic (3D) Model/Reviews |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 12.13 | Fabricated Equipment Nozzle Orientations |  |  | I/R/A I/R/A: I/R; P P: P | Long lead fabricated equipment Items only.
| 12.14 | A/G Piping Arrangement Drawings
|  | a. | Piping Transpositions to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R; P P: P | Larger than 2" shown in PDS model without valves, flanges, instrumentation, etc.
|  | b. | A/G Piping Arrangement Drawings to IFC |  | I/R/A I/R/A: I/R; P P: P
| 12.15 | Piping Isometrics to IFC | bar: P P
| 12.16 | Piping Stress Analysis
|  | a. | Preliminary Pipe Stress Analysis For Critical Lines | [10 empty] | During FEED critical lines only. | bar: P P; P P
|  | b. | Detailed Design Pipe Stress Analysis | bar: P P
| 12.17 | Steam Tracing
|  | a. | Unit Steam Headers with Dropouts Drawings to IFC | bar: P P
|  | b. | Steam Tracing Design / Isometrics to IFC | bar: P P
| 12.18 | Chemical Cleaning/Flushing / Steam Blowing
|  | a. | Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Maximum use of XXX Specifications.
|  | b. | Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 12.19 | Material Take-Off / Material Data Base
|  | a. | Piping M.T.O. | [10 empty] | Preliminary takeoff available from FEED estimate. | bar: P P; P P
|  | b. | Updates to the Piping Materials Data Base | bar: P P
|  | c. | Contractor Material Take-Offs for Contractor Buys |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 12.20 | Technical Materials Requisitions
|  | a. | Piping Valves
|  |  | - | Specialty and High Alloy Piping Valves | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Stainless Steel | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Carbon Steel, Ductile Iron, Etc. | I/A I/A: I/R/A; P P: I/R/A; R R: P | Material Requisitions by the Construction Contractor.
|  | b. | Pipe and Fittings
|  |  | - | Specialty and High Alloy Piping | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Stainless Steel | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Carbon Steel, Ductile Iron, Etc. | I/A I/A: I/R/A; P P: I/R/A; R R: P | Material Requisitions by the Construction Contractor.
|  | c. | Specialty Items
|  |  | - | Specialty and High Alloy Piping | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Stainless Steel | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Carbon Steel, Ductile Iron, Etc. | I/A I/A: I/R/A; P P: I/R/A; R R: P | Material Requisitions by the Construction Contractor.
| 12.21 | Technical Bid Evaluations
|  | a. | Piping Valves
|  |  | - | Specialty and High Alloy Piping Valves | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Stainless Steel | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Carbon Steel, Ductile Iron, Etc. | I/A I/A: I/R/A; P P: I/R/A; R R: P | Technical Bid Evaluations by the Construction Contractor.
|  | b. | Pipe and Fittings
|  |  | - | Specialty and High Alloy Piping | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Stainless Steel | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Carbon Steel, Ductile Iron, Etc. | I/A I/A: I/R/A; P P: I/R/A; R R: P | Technical Bid Evaluations by the Construction Contractor.
|  | c. | Specialty Items
|  |  | - | Specialty and High Alloy Piping | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Stainless Steel | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Carbon Steel, Ductile Iron, Etc. | I/A I/A: I/R/A; P P: I/R/A; R R: P | Technical Bid Evaluations by the Construction Contractor.
| 12.22 | As-Built Drawings (Reference Section 23.0 below)
13.0 PAINTING, INSULATION & FIREPROOFING
| 13.1 | Painting and Coatings Specifications
|  | a. | Painting and Coatings Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Painting and Coatings Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 13.2 | Insulation Specifications
|  | a. | Insulation Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Insulation Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 13.3 | Fireproofing Specifications
|  | a. | Fireproofing Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Fireproofing Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 13.4 | Material Take-Off
|  | a. | Painting and Coatings M.T.O.
|  |  | - | Equipment | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
|  |  | - | Piping | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
|  |  | - | Structural Steel | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
|  | b. | Insulation M.T.O.
|  |  | - | Equipment | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
|  |  | - | Piping | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
| 13.5 | Technical Request for Quotation
|  | a. | Paint & Coatings |  | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
|  | b. | Insulation Materials |  | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
| 13.6 | Technical Bid Evaluation and Procurement
|  | a. | Paint & Coatings |  | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
|  | b. | Insulation Materials |  | I/A I/A: I/R/A; P P: I/R/A; R R: P | By Painting Contractor -- Reviewed by Fluor
14.0 ELECTRICAL
| 14.1 | Electrical Design Basis |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
| 14.2 | General Electrical Specifications
|  | a. | General Electrical Specifications to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | General Electrical Specifications to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.3 | General Electrical Design Standards
|  | a. | General Electrical Design Standards to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | General Electrical Design Standards to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.4 | Electrical Engineering Calculations / Studies
|  | a. | Provide Motor List & IBL Power Requirements |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P
|  | b. | Relay Coordinate/Setting Records |  | I/R/A I/R/A: I/R; P P: P | EPC Scope Item
|  | c. | Load Flow Analysis |  | I/R/A I/R/A: I/R; P P: P | EPC Scope Item
|  | d. | Fault Current Calculations |  | I/R/A I/R/A: I/R; P P: P | EPC Scope Item
|  | e. | Voltage Drop Calculations |  | I/R/A I/R/A: I/R; P P: P | EPC Scope Item
|  | f. | Electical Tracing Load Calculations | [10 empty] | EPC Scope Item
|  | g. | Power Balance Calculations |  | I/R/A I/R/A: I/R; P P: P | EPC Scope Item
| 14.5 | One-Line Diagram
|  | a. | Overall System Single Line Diagram
|  |  | - | Overall System Single Line Diagram to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Overall System Single Line Diagram to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Unit Substation / ISBL Single Line Diagram
|  |  | - | Unit Substation / ISBL Single Line Diagram to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Unit Substation / ISBL Single Line Diagram to IFC | I/R/A I/R/A: I/R/A; P P: P
| 14.6 | Area Classification Drawings
|  | a. | Area Classification Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Area Classification Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.7 | Electrical Equipment Specifications
|  | a. | Power Transformer (Unit SS)
|  |  | - | Power Transformer (Unit SS) for RFQ | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Power Transformer (Unit SS) for PO | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Switchgear (Unit SS)
|  |  | - | Switchgear (Unit SS) for RFQ | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Switchgear (Unit SS) for PO | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Motor Control Centers (Unit SS)
|  |  | - | Motor Control Centers (Unit SS) for RFQ | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Motor Control Centers (Unit SS) for PO | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Uninterrupted Power System (Unit SS)
|  |  | - | Uniterrupted Power Systey (Unit SS) for RFQ | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Uniterrupted Power Systey (Unit SS) for PO | I/R/A I/R/A: I/R/A; P P: P
| 14.8 | Electrical Equipment Design
|  | a. | Plans & Sections to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Internal Wiring / Connection Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.9 | Motor List
|  | a. | Motor List to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Motor List to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.10 | Main Substation
|  | a. | Electrical System Studies |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R; P P: P | Preliminary only during FEED
|  | b. | Electrical Equipment Specifications
|  |  | - | Electrical Equipment Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Electrical Equipment Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Electrical Equipment Procurement |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Modifications Design |  | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Bulk Material Procurement |  | I/A I/A: I/R/A; P P: I/R/A; R R: P
| 14.11 | Interconnecting Power and Communications System
|  | a. | Power Feeder & Communications Electrical Design |  | I/R/A I/R/A: I/R; P P: P; I/R/A I/R/A: I/R/A; P P: P | Preliminary only. Cable tray routing conveyed in PDS model and requirements in the Scope of Facilities
|  | b. | Power Feeder & Communications Procurement |  | I/R/A I/R/A: I/R/A; P P: P
| 14.12 | Unit Substation/MCC Room
|  | a. | Transformer Yard / Building Layout
|  |  | - | Conceptual Layout | I/R/A I/R/A: I/RA; P P: P
|  |  | - | Equipment Layout to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Building Definition Specification
|  |  | - | Building Definition Specification to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Building Definition Specification to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Power Plans & Details
|  |  | - | Power Plans & Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Requirement eliminated …. part of EPC Scope
|  |  | - | Power Plans & Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Electrical Communication System
|  |  | - | Conceptual Requirements | I/R/A I/R/A: I/R/A; P P: P | Included in Scope of Facilities
|  |  | - | Electrical Communication System Drawings to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Building Lighting System Design
|  |  | - | Conceptual Requirements | I/R/A I/R/A: I/R/A; P P: P | Included in Scope of Facilities
|  |  | - | Building Lighting Plans to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | f. | Switchgear / MCC Control Logic Diagram
|  |  | - | Switchgear / MCC Control Logic Diagram to IFD | I/R/A I/R/A: I/R/A; P P: P | Requirement eliminated …. part of EPC Scope
|  |  | - | Switchgear / MCC Control Logic Diagram to IFC | I/R/A I/R/A: I/R/A; P P: P
| 14.13 | Power System Design
|  | a. | Underground Plans and Details
|  |  | - | Underground Plans and Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Requirement eliminated …. part of EPC Scope
|  |  | - | Underground Plans and Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Aboveground Plans and Details
|  |  | - | Aboveground Plans and Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Requirement eliminated …. part of EPC Scope
|  |  | - | Aboveground Plans and Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Cable Tray Plans and Details
|  |  | - | Cable Tray Plans and Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Requirement eliminated …. part of EPC Scope
|  |  | - | Cable Tray Plans and Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Schematics & Elementary Diagrams
|  |  | - | Schematics & Elementary Diagrams to IFD | I/R/A I/R/A: I/R/A; P P: P | Requirement eliminated …. part of EPC Scope
|  |  | - | Schematics & Elementary Diagrams to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Connection Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | f. | Power Cable Schedules to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.14 | Grounding System Design
|  | a. | Grounding System Calculations
|  |  | - | Initial | I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Final | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Grounding Plans & Details
|  |  | - | Grounding Plans & Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Grounding Plans & Details to IFC | I/R/A I/R/A: I/R/A; P P: P
| 14.15 | Lighting System Design
|  | a. | Lighting Plans & Details
|  |  | - | Lighting Plans & Details to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Lighting Plans & Details to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Lighting Panel Board Schedule to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Connection Diagrams to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Emergency Lighting Plan to IFC |  | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Aircraft Warning Lights to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.16 | Electrical Heat Tracing (Plans & Details)
|  | a. | Design Basis Established |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Electrical Heat Tracing (Plans & Details) to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.17 | Cathodic Protection & Lightning Protection System
|  | a. | Design Basis Established |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Cathodic Protection & Lightning Protection System to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.18 | Tie-Ins
|  | a. | Design Basis & Tie-In List |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Refer to XXX specification requirements & Scope of Facilities for design basis. Electrical tie-in list required.
|  | b. | Electrical Tie-In Plans & Details to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 14.19 | Material Take-Off
|  | a. | Electrical Materials |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Unit Substation Materials |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Main Station to Unit SS |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Consolidated MTO |  | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Spool (Drum) Schedule |  | I/R/A I/R/A: I/R/A; P P: P
| 14.20 | Technical Request for Quotation
|  | a. | Electrical Equipment (long lead / critical) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Long leads and critical items to be identified during FEED
|  | b. | Special & U/G Cables |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Unit Substation |  | I/R/A I/R/A: I/R/A; P P: P
| 14.21 | Technical Bid Evaluations
|  | a. | Unit Electrical Equipment |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Special & U/G Cables (IBL) |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Unit Substation |  | I/R/A I/R/A: I/R/A; P P: P
| 14.22 | Review Vendor Data |  |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 14.23 | As-Built Drawings (Reference Section 23.0 below)
15.0 INSTRUMENTATION & CONTROLS
| 15.1 | Instrument General Design Requirements
|  | a. | Instument & Controls Design Basis to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  | b. | Automation Functional Requirements Specification
|  |  | - | Automation Functional Requirements Spec. to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in the Scope of Facilities and DCS Functional Specification
|  |  | - | Automation Functional Requirements Spec. to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | General Notes, Symbols & Legend
|  |  | - | General Notes, Symbols & Legend to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in EFD Legend Sheets
|  |  | - | General Notes, Symbols & Legend to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Instrumentation Design Standards
|  |  | - | Instrumentation Design Standards to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Instrumentation Design Standards to IFC | I/R/A I/R/A: I/R/A; P P: P
| 15.2 | Instrument Material Specifications
|  | a. | Special Instrumentation Descriptions
|  |  | - | Special Instrument Descriptions to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Special Instrument Descriptions to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Detailed Instrument Material Specs.
|  |  | - | Detailed Instrument Material Specs. to IFD | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for FEED.
|  |  | - | Detailed Instrument Material Specs. to IFC | I/R/A I/R/A: I/R/A; P P: P
| 15.3 | Instrument Data Sheets (General)
|  | a. | Process Design Conditions |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Preliminary Sizing |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Final Sizing |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Instrument Numbering |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 15.4 | Relief Valve Specifications
|  | a. | Process and Design Conditions |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Preliminary Sizing |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Final Sizing |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Instrument Numbering |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 15.5 | Control Valve Sizing/Specifications
|  | a. | Process and Design Conditions |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Preliminary Sizing |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Final Sizing |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Instrument Numbering |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 15.6 | Flow Meter Sizing/Specifications
|  | a. | Process and Design Conditions |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Preliminary Sizing |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Final Sizing |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Instrument Numbering |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 15.7 | Analyzers
|  | a. | Design Specification
|  |  | - | Design Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Design Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Field Check-0ut |  | I/A I/A: I/R/A; P P: S; R R: P
| 15.8 | Distributed Control System (DCS) and Rack Room Equipment (Unit Control Room Only)
|  | a. | DCS Point Count, Card Count and Type |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in the DCS Design Specification.
|  | b. | Design Specification
|  |  | - | Design Specification to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Design Specification to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Configuration |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P | Configuration by Supplier
|  | d. | Factory Testing |  |  |  | I/R/A | I/R/A | P | I/R/A |  | P | I | FAT by Supplier
|  | e. | Field Check-Out |  | I/A I/A: I/R/A; P P: P; R R: I | With Assistance from Supplier
| 15.9 | Safety Interlock System (SIS)
|  | a. | SIS Point Count, Card Count and Type |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in the SIS Design Specification
|  | b. | Design Specification
|  |  | - | Design Specification to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Design Specification to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Configuration |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P | Configuration by Supplier
|  | d. | Factory Testing |  |  |  | I/R/A | I/R/A | P | I/R/A |  | P | I | FAT by Supplier
|  | e. | Field Check-Out |  | I/A I/A: I/R/A; P P: P; R R: I | With Assistance from Supplier
| 15.10 | Main Control Room
|  | a. | Control Room Layout
|  |  | - | Control Room Layout to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  |  | - | Control Room Layout to IFC | I/R/A I/R/A: I/R/A; P P: P
| 15.11 | DCS Configuration
|  | a. | DCS Interface Philosophy |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: I/R/A; R R: I | Narrative description only during FEED
|  | b. | DCS Equipment Specifications
|  |  | - | DCS Equipment Specifications to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P; R R: I
|  |  | - | DCS Equipment Specifications to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | DCS Equipment Procurement |  | I/R/A I/R/A: I/R/A; P P: P | Up to and including review of bids and supplier recomendation only.
|  | d. | DCS Installation Designs to IFC |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P
|  | e. | Interconnecting Data Highway Design, Specification, and Procurement |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P
|  | f. | Hard Wired Interconnecting S/D from Operator Shelter Rack Room J-Box to Main Control/Rack Room |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P
| 15.12 | Operator Shelter & DCS Rack Room
|  | a. | Conceptual Layout |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities
|  | b. | Operator Shelter/Rack Room Equipment Layout
|  |  | - | Operator Shelter/Rack Room Equipment Layout to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P; R R: I
|  |  | - | Operator Shelter/Rack Room Equipment Layout to IFC | I/R/A I/R/A: I/R/A; P P: P; R R: I
|  | c. | DCS/Rack Room Equipment Location Plans & Details
|  |  | - | DCS/Rack Room Equipment Layout Plans & Details to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P; R R: I | Preliminary only.
|  |  | - | DCS/Rack Room Equipment Layout Plans & Details to IFC | I/R/A I/R/A: I/R/A; P P: P; R R: I
|  | d. | DCS to Operator Console Wiring Plans & Connection Drawings
|  |  | - | DCS to Operator Console Wiring Plans & Connection Drawings to IFD | I/R/A I/R/A: I/R/A; P P: P; R R: I | Requirement eliminated …. part of EPC Scope
|  |  | - | DCS to Operator Console Wiring Plans & Connection Drawings to IFC | I/R/A I/R/A: I/R/A; P P: P; R R: I
|  | f. | DCS to Marshalling Panel Wiring Plans & Details
|  |  | - | DSC to Marshalling Panel Wiring Plans & Details to IFD | I/R/A I/R/A: I/R/A; P P: P; R R: I | Requirement eliminated …. part of EPC Scope
|  |  | - | DCS to Marshalling Panel Wiring Plans & Details to IFC | I/R/A I/R/A: I/R/A; P P: P; R R: I
|  | g. | IBL JB to Rack Room Cable/Ductway Routing Layout
|  |  | - | IBL JB to Rack Room Cable/Ductway Routing Layout to IFD | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P; R R: I | Preliminary only.
|  |  | - | IBL JB to Rack Room Cable/Ductway Routing Layout to IFC | I/R/A I/R/A: I/R/A; P P: P; R R: I
|  | h. | IBL JB to Rack Room Cable/Ductway Plans & Details
|  |  | - | IBL JB to Rack Room Cable/Ductway Plans & Details to IFD | I/R/A I/R/A: I/R/A; P P: P; R R: I | Requirement eliminated …. part of EPC Scope
|  |  | - | IBL JB to Rack Room Cable/Ductway Plans & Details to IFC | I/R/A I/R/A: I/R/A; P P: P; R R: I
|  | i. | IBL JB to Rack Room Connection Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P
|  | j. | Hard Wired Interconnecting S/D Wiring From Rack to J-Box to IFC |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P
| 15.13 | Local Control Panel Layout |  |  | I/R/A I/R/A: I/R/A; P P: I/R/A; R R: P
| 15.14 | Instrument List (Index)
|  | a. | Instrument List (Index) to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Instrument List (Index) to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 15.15 | Cause and Efffect Diagram
|  | a. | Cause and Effect Diagram to IFD |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Philosophy developed along with Process group only during FEED. No configuration and no programming.
|  | b. | Cause and Effect Diagram to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 15.16 | Instrument Installation Assemblies
|  | a. | Instrument Installation Assemblies to IFD |  | I/R/A I/R/A: I/R/A; P P: P | Scope of Facilities with listing of XXX requirements / specs for similar requirements for FEED. Fluor to develop for unique requirements.
|  | b. | Instrument Installation Assemblies to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 15.17 | Instrument Location Plans, including:
|  | a. | Key Plan
|  |  | - | Key Plan to IFD | I/R/A I/R/A: I/R/A; P P: P; R R: I | Requirement eliminated …. part of EPC Scope
|  |  | - | Key Plan to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | b. | All Field Instruments
|  |  | - | Field Instruments to IFD | I/R/A I/R/A: I/R/A; P P: P; R R: I | Requirement eliminated …. part of EPC Scope
|  |  | - | Field Instruments to IFC | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Gas Detectors & Alarms
|  |  | - | Gas Detectors & Alarms to IFD | I/R/A I/R/A: I/R/A; P P: P; R R: I | Requirement eliminated …. part of EPC Scope
|  |  | - | Gas Detectors & Alarms to IFC | I/R/A I/R/A: I/R/A; P P: P
| 15.18 | Instrument Installation Drawings
|  | a. | Instrument Installation Drawings to IFD |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Instrument Installation Drawings to IFC |  | I/R/A I/R/A: I/R/A; P P: P
| 15.19 | Instrument Connection Diagrams to IFC |  |  | I/R/A I/R/A: I/R/A; P P: P
| 15.20 | Instrument Wire List/Schedule to IFC |  |  | I/R/A I/R/A: I/R/A; P P: P
| 15.21 | Instrument Loop Diagrams to IFC |  |  | I/R/A I/R/A: I/R/A; P P: P
| 15.22 | Vendor Package Control Diagrams to IFC |  |  | I/R/A I/R/A: I/R/A; P P: P | Vendor Control Diagrams by Vendor
| 15.23 | Vendor Package Equip P&IDs |  |  | I/R/A I/R/A: I/R/A; P P: P | Vendor Package EFD's by Vendor
| 15.24 | Bulk Material Take-Off |  |  | I/R/A | P | I/R/A | P |  | I/R/A |  | I/R/A | P | Preliminary takeoff available from FEED estimate.
| 15.25 | Technical Request for Quotation (IBL) Packages
|  | a. | Specialty Equipment and Instruments |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Non-Specialty Instruments |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | General Bulk Materials |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: I/R/A; R R: P
| 15.26 | Technical & Commercial Bid Evaluations
|  | a. | Specialty Equipment and Instruments |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Non-Specialty Instruments |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | General Bulk Materials |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: I/R/A; R R: P
| 15.27 | Review Vendor Data |  |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 15.28 | As-Built Drawings (Reference Section 23.0 below)
16.0 PROJECT MANAGEMENT & SUPPORT
| 16.1 | Establish/Administer Contracts
|  | a. | CEP Contract
|  | b. | FEED Contract | bar: I/R/A I/R/A to P P
|  | c. | Detailed EPC Contract | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 16.2 | Overall Project Planning
|  | a. | Establish Overall Schedule |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | b. | Estab. Project Control Milestones |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | c. | Organization & Staffing |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | d. | Work Responsibilities |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | e. | Alignment Process
|  |  | - | Develop Project Purpose Statement | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  |  | - | Establish & Maintain the Project Critical To Quality (CTQs) Metrics | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
| 16.3 | Project Execution Plan (PEP)
|  | a. | Establish & Issue PEP |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Design Execution Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | c. | Project Automation Plan |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | d. | Project Quality Plan |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 16.4 | Project Procedures Manual (PPM)
|  | a. | Establish & Issue PPM |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Project Mgmt & Admin Procedures |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Engrg & Procurement Procedures |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 16.5 | Project Scope Definition
|  | a. | Establish Initial Scope |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | b. | Estab. Deviation Procedures |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | c. | Maintain Scope Control |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | d. | Establish Initial Control Base |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
| 16.6 | Project Reporting
|  | a. | Project Progress Reports |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Quarterly Management Reports |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Final Project Reports |  | P P: I; P P: P; I/A I/A: I/R/A; P P: P
| 16.7 | Project Files/Correspondence Records
|  | a. | Establish Project File Index | bar: P P; P P; P P
|  | b. | Estab./Maintain Corresp. Logs | bar: P P; P P; P P
|  | c. | Maintain Project Files | bar: P P; P P; P P
|  | d. | Distribution Matrix | bar: P P; P P; P P
| 16.8 | Project Completion / Turnover
|  | a. | Conceptual Engineering
|  | b. | Basic Engineering | bar: I/R/A I/R/A to P P
|  | c. | Detailed Engineering & Procurement | bar: I/R/A I/R/A to P P
|  | e. | Construction, Commissioning & Turnover | bar: I/A I/A; P P
|  | f. | Project Closeout | bar: I/A I/A; P P
| 16.9 | Project Constructability Program
|  | a. | Establish Constructability Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Constructability Reviews |  | I/R/A | P | I/A | P |  | I/A | I | P | I
|  | c. | Constructability Documentation | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 16.10 | Project Value Awareness Program
|  | a. | Establish Value Awareness Program |  | I/A | P | I/A | P | I | I/A | I | P | I
|  | b. | Value Awareness Documentation |  | I/A | P | I/A | P |  | I/A |  | P
|  | c. | Employee Recognition Program
|  |  | - | Employee Recognition | bar: I/R/A I/R/A to P P; I/A I/A; P P
|  |  | - | Team Recognition | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 16.11 | Taxes
|  | a. | Sales Tax/VAT | bar: I/R/A I/R/A to P P; I/A I/A; P P
|  | b. | Local & Govt. Sales Tax | bar: I/R/A I/R/A to P P; I/A I/A; P P
17.0 PROJECT CONTROLS
| 17.1 | Overall Project Planning
|  | a. | Establish Overall Schedule |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | b. | Estab. Project Control Milestones |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | c. | Organization & Staffing |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | d. | Work Responsibilities |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
| 17.2 | Project Schedules (Gantt Charts)
|  | a. | Establish & Maintain the Management Summary Schedule |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
|  | b. | Establish & Maintain the CEP Schedule
|  | c. | Establish & Maintain the FEED Schedule |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | d. | Establish & Maintain the EPC Schedule |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P | S
| 17.3 | Project Reporting
|  | a. | Cost Reporting and Control
|  |  | - | Commitments & Expenditures | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  |  | - | Current Budget | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  |  | - | Cost Forecasts | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Effort Productivity
|  |  | - | Forecasted Percent Complete | P P: P; I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  |  | - | Earned Percent Complete | P P: P; I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 17.4 | Total Installed Cost Estimates
|  | a. | Estimate Execution Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | +/- 35% Estimate
|  | c. | +/- 10% Definitive Estimate |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Subcontractor Check Estimates |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | e. | Material Take-Off Documentation |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 17.5 | Project Change Management
|  | a. | Establish Procedures |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Monthly Reporting |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Cost Estimating |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | d. | Maintain Project Change Log |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 17.6 | Monthly Invoices
|  | a. | Assemble Labor Costs |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Assemble Expenses |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Assemble XXX Costs |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 17.7 | Project Close-out |  |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
18.0 TECHNICAL DOCUMENT CONTROL
| 18.1 | Distribution Matrices
|  | a. | Specifications |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Engineering Data/Drawings |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Supplier Data |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 18.2 | Document Control System
|  | a. | Specifications & Drawings |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Supplier Data |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 18.3 | Document Control, Receiving, Issuing |  |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 18.4 | Turnover of Documents
|  | a. | Engineering Drawings |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Supplier Data/Drawings |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | c. | Mechanical Catalogs |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
19.0 PROJECT INFORMATION MANAGEMENT
| 19.1 | Define PDS/CAD Design Systems |  |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 19.2 | Define Software Utilization Plan |  |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 19.3 | Telecommunications
|  | a. | Define/Implement Secure E-Mail System |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Define Extranet Requirements |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Determine Needs for Each Location |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | d. | Implement Extranet |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 19.4 | Define Electronic Deliverables |  |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 19.5 | Define Worksharing Requirements
|  | a. | Analyze Scope for Each Location |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Define Critical Execution Tools |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | c. | Implement Execution Tools |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
| 19.6 | Project Close-out
|  | a. | Define Close-out Procedure |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
|  | b. | Execute Close-out |  | I/R/A | P | I/R/A | P |  | I/R/A |  | P
20.0 MATERIALS MANAGEMENT
| 20.1 | Materials Management Plan |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 20.2 | Materials Management Procedures |  |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Included in Material Management Plan.
| 20.3 | Project Master Bidders List
|  | a. | Initiate Supplier List |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Supplier Selection - Full Bidders List |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
| 20.4 | Long Lead / Critical Equipment List
|  | a. | Establish Criteria |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Establish Long Lead / Critical Equipment List |  | I/R/A I/R/A: I/R/A; P P: P
| 20.5 | Requests for Quotation (RFQ)
|  | a. | Prepare RFQ Packages |  | I/R/A I/R/A: I/R/A; P P: P
|  | b. | Issue RFQs to Bidders |  | I/R/A I/R/A: I/R/A; P P: P
|  | c. | Prepare RFQ Supplements |  | I/R/A I/R/A: I/R/A; P P: P
|  | d. | Issue RFQ Supplements |  | I/R/A I/R/A: I/R/A; P P: P
|  | e. | Prepare and Issue RFQ Packages (Long Lead Equipment) |  | I/R/A I/R/A: I/R/A; P P: P
|  | f. | Prepare and Issue RFP for Early Site Contracts |  | I/R/A I/R/A: I/R/A; P P: P
| 20.6 | Bid Evaluations & Summaries
|  | a. | Technical Evaluations |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | b. | Bid Clarifications/Meetings |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | c. | Commercial Evaluations |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | d. | Bid Summary & Recommendation |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | e. | Bid Evaluation and Recommenditions (Long Lead Equipment) |  | I/R/A I/R/A: I/R/A; P P: P
|  | f. | Bid Evaluation and Recommendations for Early Site Contracts |  | I/R/A I/R/A: I/R/A; P P: P
| 20.7 | Purchase Orders
|  | a. | Issue "FAX" Commitments |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | b. | Prepare Purchase Order | bar: P P; P P
|  | c. | Issue Formal P.O. |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | d. | Maintain Project P.O. Files | bar: P P; I/A I/A; P P
|  | e. | Procurement Records (Turnover to XXX) |  | I/A I/A: I/R/A; P P: P
|  | f. | Prepare & Issue P.O. (Long Lead Equipment) |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P | Prepared but not issue to selected supplier until EPC.
|  | g. | Prepare and Issue Contracts for Early Site Contracts |  | I/R/A I/R/A: I/R/A; P P: P
| 20.8 | Spare Parts List and Procurement
|  | a. | Establish Spare Parts Philosophy |  | I/R/A I/R/A: I/R/A; P P: P; I/R/A I/R/A: I/R/A; P P: P
|  | b. | Provide Spare Parts Recommendations and Pricing
|  |  | - | Construction & Startup |  |  | I/R/A | P | I | I/R/A |  | P | S | Construction contractors for bulk spare parts.
|  |  | - | Capital (Investment) Spares | I/R/A | P | I/R/A | P | I | I/R/A |  | P |  | Long lead equipment during FEED.
|  | c. | Submit Supplier Spare Parts Lists/Quotations to XXX |  | I/R/A I/R/A: I/R/A; P P: P; P P: P | Long lead equipment during FEED.
|  | d. | Procure Spare Parts
|  |  | - | Construction & Startup | I/A I/A: I/R/A; P P: P; R R: S | Construction contractors for bulk spare parts.
|  |  | - | Capital (Investment) Spares | I/R/A | P | I/R/A | P |  | I/R/A |  | P |  | Prepared but not issued to selected suppliers until EPC for long lead equipment.
| 20.9 | Expediting
|  | a. | Supplier Engineering Data |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | b. | Fabrication and Equipment/Material Deliveries |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | c. | Report Status of Orders |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 20.10 | Supplier Quality Surveillance
|  | a. | Develop Project Inspection Plan |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | b. | Identify Inspection Requirements |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | c. | Conduct Pre-Inspection Mtgs. |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | d. | Perform Shop Inspection |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | e. | Inspection Reports/Followup |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 20.11 | Logistics
|  | a. | Offshore Inland Transportation | bar: P P to R R
|  | b. | Export Packer | bar: P P to R R
|  | c. | Freight Forwarder | bar: P P to R R
|  | d. | Marine Transportation | bar: P P to R R
|  | e. | Onshore Inland Transportation | bar: P P to R R
|  | f. | Heavy Lift Handling & Transport as Required | bar: P P to R R
| 20.12 | Customs Clearance | bar: P P to R R
| 20.13 | Customs Duties | bar: P P to R R
| 20.14 | Insurance (Marine & Freight) | bar: I/A I/A
| 20.15 | Supplier Invoices
|  | a. | Review Invoices |  | I/A I/A: R; P P: P; R R: S
|  | b. | Pay Invoices |  | I/A I/A: R; P P: P; R R: S
|  | c. | Supplier Backcharges
|  |  | - | Initiate Back Charges | I/A I/A: R; P P: P; R R: S
|  |  | - | Verify Back Charges | I/A I/A: R; P P: P; R R: S
|  |  | - | Administrative Back Charge | I/A I/A: R; P P: P; R R: S
| 20.16 | Procurement Status Systems/Reports (Inquiry through P.O.)
|  | a. | P.O. through Delivery ("Material Status Reports") |  | I/R/A I/R/A: R; P P: P; I/A I/A: R; P P: P; R R: S | EPC for EPC furnished materials & equipment
|  | b. | Composite Material Status Reports to Site and "Site Received" Status Reporting |  | I/R/A I/R/A: R; P P: P; I/A I/A: R; P P: P; R R: S | EPC for EPC furnished materials & equipment
| 20.17 | Materials Management Site Activities
|  | a. | Receive Material and Equipment |  | I/A I/A: R; P P: P; R R: S | EPC for EPC furnished materials & equipment
|  | b. | Issue Receiving Reports | [10 empty] | EPC for EPC furnished materials & equipment | bar: P P to R R
|  | c. | Proper Storage of Material and Equipment |  | I/A I/A: R/A; P P: P; R R: S | EPC for EPC furnished materials & equipment
|  | d. | Disburse Material and Equipment | [10 empty] | EPC for EPC furnished materials & equipment | bar: P P to R R
21.0 CONTRACT ADMINISTRATION
| 21.1 | Contract RFP/PO Language |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.2 | Contracts Authorization Approval
|  | a. | Matrix (RFP) |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.3 | Contracts Listing (Packages) |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.4 | Contract(s) Material Responsibility Matrix |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.5 | Contractor Bid List |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.6 | Contractor Single Source Authorization |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.7 | Contractor Work Package(s) |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.8 | Contracts Status Reports |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.9 | Contactor Bid Tabs / Contract Award |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.10 | Contract Hard Copy (Notice of Award) |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.11 | Approval for Contract Modification |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.12 | Contract Modification Hard Copy |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 21.13 | Contractor Backcharge |  |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
22.0 PERMITTING
| 22.1 | Overall Coordination | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 22.2 | Formation of the Environmental Impact Dossier | bar: I/R/A I/R/A to P P
| 22.3 | Environmental Impact Assessment | bar: I/R/A I/R/A to P P
| 22.4 | Technical Dossier
|  | a. | Electrical | bar: I/R/A I/R/A to P P
|  | b | Pressure Vessels | bar: I/R/A I/R/A to P P
|  | c | Chemical Storage | bar: I/R/A I/R/A to P P
|  | d. | Storm Water | bar: I/R/A I/R/A to P P
|  | e. | Liquid Process Waste | bar: I/R/A I/R/A to P P
|  | f. | Gaseous Process Waste | bar: I/R/A I/R/A to P P
|  | g. | Solid Process Waste | bar: I/R/A I/R/A to P P
| 22.5 | Project Authorization | bar: I/R/A I/R/A to P P; I/A I/A; P P
| 22.6 | Construction Dossier
|  | a. | Electrical |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | b. | Water |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | c. | Sanitary |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
|  | d. | Storm Water |  | I/R/A I/R/A: I/R/A; P P: P; I/A I/A: I/R/A; P P: P
| 22.7 | Building Permit Application Package | bar: I/R/A I/R/A to P P
| 22.8 | Installation Permits | bar: I/A I/A; P P
| 22.9 | Activity License | bar: I/A I/A; P P
23.0 CONSTRUCTION SUPPORT
| 23.1 | Construction Overall Planning
|  | a. | Overall Schedule |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
|  | b. | Contract Planning |  | I/R/A I/R/A: R/I/A; P P: P; I/A I/A: R/I/A; P P: P
| 23.2 | Construction Packages
|  | a. | Plan & Procedures |  | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | b. | Engineering Release Packages |  | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | c. | Bidders List |  | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | d. | Contract Packages
|  |  | - | Technical Definition | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  |  | - | Construction Requirements | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  |  | - | Commercial Requirements | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | e. | Technical Bid Evaluation |  | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | f. | Commercial Bid Evaluation |  | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | g. | Field Construction Administration |  | I/A I/A: R/A; P P: P
|  | h. | Invoice Verification |  | I/A I/A: R/A; P P: P
|  | i. | Invoice Payment |  | I/A I/A: R/A; P P: P
| 23.3 | Engineering Support During Construction
|  | a. | Clarifications/Question Resolution |  | I/R/A I/R/A: R/A; P P: P; I/A I/A: R/A; P P: P
|  | b. | Site Engineering Support
|  |  | - | Process Engineer | bar: P P; P P
|  |  | - | Structural Engineer | bar: P P; P P
|  |  | - | Piping | bar: P P; P P
|  |  | - | Electrical | bar: P P; P P
|  |  | - | Instrumentation & Controls | bar: P P; P P
| 23.4 | Construction Changes/Claims Administration
|  | a. | Review Contractor Claims for validity of Design Change |  | I/A I/A: R/A; P P: P
|  | b. | Review Contractor Claims for pricing validity |  | I/A I/A: R/A; P P: P
|  | c. | Claims Approval and Administration |  | I/A I/A: R/A; P P: P
| 23.5 | Construction Hydrotest Planning, Performance, and Checkout
|  | a. | Hydrotest Flow Diagrams |  | I/A I/A: R/A; P P: P; R R: I
|  | b. | Prepare Hydrotest Packages |  | I/A I/A: R/A; P P: P; R R: I
|  | c. | Perform Hydrotest |  | I/A I/A: R/A; P P: P; R R: I
|  | d. | Hydrotest punchlist |  | I/A I/A: R/A; P P: P; R R: I
|  | e. | Punchlist Corrections/Completions |  | I/A I/A: R/A; P P: P; R R: I
|  | f. | Hydrotest System Signoff | bar: I/A I/A; P P to R R
| 23.6 | Mechanical Completion Checkout Support
|  | a. | Process Engineering |  | I/A I/A: R/A; P P: S; R R: P
|  | b. | Piping |  | I/A I/A: R/A; P P: S; R R: P
|  | c. | Electrical |  | I/A I/A: R/A; P P: S; R R: P
|  | d. | Instrumentation and Controls |  | I/A I/A: R/A; P P: S; R R: P
| 23.7 | As-Built Drawing Updates
|  | a. | Obtain Construction Contractor As-Built Markups |  | I/A I/A: R/A; P P: P
|  | b. | Draft As-Built Revisions and Turnover to XXX
|  |  | - | EFD's | I/A I/A: R/A; P P: P; R R: I
|  |  | - | Plot Plans | I/A I/A: R/A; P P: P; R R: I
|  |  | - | U.G. Piping Drawings | I/A I/A: R/A; P P: P; R R: I
|  |  | - | One Line Diagrams | I/A I/A: R/A; P P: P; R R: I
|  |  | - | U.G. Electrical Drawings | I/A I/A: R/A; P P: P; R R: I
|  |  | - | Electrical Schematics | I/A I/A: R/A; P P: P; R R: I
|  |  | - | Loop Diagrams | I/A I/A: R/A; P P: P; R R: I
|  |  | - | Instrument Connection Diagrams | I/A I/A: R/A; P P: P; R R: I
24.0 CONSTRUCTION MANAGEMENT SERVICES & CONSTRUCTION
| 24.1 | Construction Overall Planning |  |  | I/A I/A: R/A; P P: P
| 24.2 | Detailed Construction Scheduling |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.3 | Temporary Facilities
|  | a. | Offices |  | I/A I/A: R/A; P P: P
|  | b. | Roads |  | I/A I/A: R/A; P P: P
|  | c. | Fences & Gates |  | I/A I/A: R/A; P P: P
|  | d. | Utilities | bar: I/A I/A
|  | e. | Craft Parking |  | I/A I/A: R/A; P P: P
|  | f. | Warehousing |  | I/A I/A: R/A; P P: P
| 24.4 | Site Safety |  |  | I/A I/A: R/A; P P: P
| 24.5 | Site Security | bar: I/A I/A
| 24.6 | Material Management (Field Warehouse) |  |  | I/A I/A: R/A; P P: P | For EPC Contractor funished equipment & materials.
| 24.7 | Insurance Costs on Site | bar: I/A I/A
| 24.8 | Secretarial Services at Site |  |  | I/A I/A: R/A; P P: P
| 24.9 | Office Furniture & Copying Machines |  |  | I/A I/A: R/A; P P: P
| 24.10 | Contract Administration Activities |  |  | I/A I/A: R/A; P P: P
| 24.11 | Site Construction Supervision |  |  | I/A I/A: R/A; P P: P
| 24.12 | Site Construction, All Crafts and Disciplines |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.13 | Rigging Activities Support |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.14 | Construction Equipment and Tools |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.16 | Site Quality Control |  |  | I/A I/A: R/A; P P: P
| 24.17 | Site Quality Control / Checking Field Welding Procedures |  |  | I/A I/A: R/A; P P: P
| 24.18 | Tie-Ins
|  | a. | Purchasing |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
|  | b. | Installation |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.19 | Field Progress Reporting |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.20 | Clean-Up and Test |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors.
| 24.21 | Construction Turnover Package Identification |  |  | I/A I/A: R/A; P P: P; R R: R
| 24.22 | Construction Turnover Packages |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.23 | Lubricants Tabulation Requirements |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
| 24.24 | Purchase & Charge Lubricants |  |  | I/A I/A: R/A; P P: R/A; R R: P | Construction Contractors
25.0 COMMISSIONING & STARTUP
| 25.1 | Operating Manuals | [11 empty] | Equipment Suppliers | bar: I/R/A I/R/A to I/A I/A; P P to R R
| 25.2 | Lab Procedures and Equipment Recommendations | bar: I/R/A I/R/A to P P; I/A I/A to P P
| 25.3 | Instrument Loop Check |  |  | I/A I/A: R/A; P P: R/A; R R: P
| 25.4 | Operator Training | bar: I/R/A I/R/A to P P; I/A I/A to P P
| 25.5 | Commissioning / Start Up Procedures | bar: I/R/A I/R/A to P P; I/A I/A to P P
| 25.6 | Commissioning / Start Up Execution | bar: I/A I/A
| 25.7 | Performance Test | bar: I/A I/A